## OOM Cost Estimating
Note: Shaded areas are calculated automatically after unshaded areas are filled in.
| Estimated Direct Labor Hours = | 0 | hours
| Composite Burdened Labor Rate = | 0 | per hour
| Target Profit = | 0%
|  | With Profit | Without Profit
| Estimated Direct Cost | 0 | 0
| Target Profit | 0
| Estimated Total Price | 0 | 0
| OOM Minimum Price | 0 | 0
| OOM Maximum Price | 0 | 0
Note on D7: Estimate the total number of direct labor hours and round up.
Note on D8: This composite burdened labor rate can usually be obtained from your corporate finance group.
Note on D9: Insert a targeted profit rate or a minimum-attractive-rate of-return (MARR).
Order of Magnitude (OOM) Cost Calculator

## Budgetary Estimating
Note: Shaded areas are calculated automatically after unshaded areas are filled in.
|  |  | 1Q06 |  | 2Q06 |  | 3Q06 |  | 4Q06 |  | 1Q06 |  | 2Q06 |  | 3Q06 |  | 4Q06 |  |  | TOTAL
WBS Level 2 |  | Labor | Equivalent | Direct | Equivalent | Direct | Equivalent | Direct | Equivalent | Direct | Equivalent | Direct | Equivalent | Direct | Equivalent | Direct | Equivalent | Direct |  | DIRECT
Activity | Labor Category | ID Code | People Rq'd | Cost | People Rq'd | Cost | People Rq'd | Cost | People Rq'd | Cost | People Rq'd | Cost | People Rq'd | Cost | People Rq'd | Cost | People Rq'd | Cost |  | COST
Activity | Project Manager | 100 | 0.33 | 9438 | 0.33 | 9438 | 0.33 | 9438 | 0.33 | 9438 | 0.33 | 9815.52 | 0.33 | 9815.52 | 0 | 0 | 0 | 0 |  | 57383.04
"A" | Sr. Systems Engineer | 110 | 0.33 | 7722 | 0.33 | 7722 | 0.33 | 7722 | 0.33 | 7722 | 0.33 | 8030.88 | 0.33 | 8030.88 | 0 | 0 | 0 | 0 |  | 46949.76
| Systems Engineer | 112 | 0.5 | 11180 | 0.7 | 15652 | 0.8 | 17888 | 0.8 | 17888 | 0.5 | 11627.2 | 0.3 | 6976.32 | 0 | 0 | 0 | 0 |  | 81211.52
| Sr. Design Engineer | 120 | 0.5 | 11700 | 2 | 46800 | 2 | 46800 | 2 | 46800 | 0.5 | 12168 | 0.4 | 9734.4 | 0 | 0 | 0 | 0 |  | 174002.4
| Software Engineer | 122 | 0.25 | 5720 | 0.75 | 17160 | 1 | 22880 | 1 | 22880 | 0.25 | 5948.8 | 0.5 | 11897.6 | 0 | 0 | 0 | 0 |  | 86486.4
| Quality Control | 124 | 0.33 | 5834.4 | 0.33 | 5834.4 | 0.5 | 8840 | 0.5 | 8840 | 0.33 | 6067.776 | 1 | 18387.2 | 0 | 0 | 0 | 0 |  | 53803.776
| Design Engineer | 125 | 2 | 44200 | 2 | 44200 | 3 | 66300 | 2 | 44200 | 1 | 22984 | 1 | 22984 | 0 | 0 | 0 | 0 |  | 244868
| Associate Design Engineer | 127 | 2 | 36400 | 3 | 54600 | 3 | 54600 | 3 | 54600 | 2 | 37856 | 1 | 18928 | 0 | 0 | 0 | 0 |  | 256984
| Sr. Test Engineer | 130 | 0 | 0 | 0 | 0 | 1 | 23920 | 1 | 23920 | 1 | 24876.8 | 3 | 74630.4 | 0 | 0 | 0 | 0 |  | 147347.2
| Test Engineer | 135 | 0 | 0 | 0 | 0 | 2 | 45760 | 2 | 45760 | 4 | 95180.8 | 5 | 118976 | 0 | 0 | 0 | 0 |  | 305676.8
| Project Coordinator | 140 | 0.33 | 6349.2 | 1.2 | 23088 | 1.5 | 28860 | 1.5 | 28860 | 1 | 20009.6 | 0.7 | 14006.72 | 0 | 0 | 0 | 0 |  | 121173.52
| Configuration Management | 142 | 0.33 | 6349.2 | 0.7 | 13468 | 1 | 19240 | 1 | 19240 | 0.5 | 10004.8 | 0.7 | 14006.72 | 0 | 0 | 0 | 0 |  | 82308.72
| Business Manager | 150 | 0.33 | 6520.8 | 0.5 | 9880 | 1 | 19760 | 1 | 19760 | 0.5 | 10275.2 | 0.5 | 10275.2 | 0 | 0 | 0 | 0 |  | 76471.2
| Activity "A" Subtotal |  | 7.23 | 151413.6 | 11.84 | 247842.4 | 17.46 | 372008 | 16.46 | 349908 | 12.24 | 274845.376 | 14.76 | 338648.96 | 0 | 0 | 0 | 0 |  | 1734666.336
|  |  | 1Q06 |  | 2Q06 |  | 3Q06 |  | 4Q06 |  | 1Q06 |  | 2Q06 |  | 3Q06 |  | 4Q06 |  |  | TOTAL
WBS Level 2 |  | Labor | Equivalent | Direct | Equivalent | Direct | Equivalent | Direct | Equivalent | Direct | Equivalent | Direct | Equivalent | Direct | Equivalent | Direct | Equivalent | Direct |  | DIRECT
Activity | Labor Category | ID Code | People Rq'd | Cost | People Rq'd | Cost | People Rq'd | Cost | People Rq'd | Cost | People Rq'd | Cost | People Rq'd | Cost | People Rq'd | Cost | People Rq'd | Cost |  | COST
Activity | Project Manager | 100 | 0.33 | 9438 | 0.33 | 9438 | 0.33 | 9438 | 0.33 | 9438 | 0.33 | 9815.52 | 0.33 | 9815.52 | 0 | 0 | 0 | 0 |  | 57383.04
"B" | Sr. Systems Engineer | 110 | 0.33 | 7722 | 0.33 | 7722 | 0.33 | 7722 | 0.33 | 7722 | 0.33 | 8030.88 | 0.33 | 8030.88 | 0 | 0 | 0 | 0 |  | 46949.76
| Systems Engineer | 112 | 0.5 | 11180 | 0.7 | 15652 | 0.8 | 17888 | 0.8 | 17888 | 0.5 | 11627.2 | 0.3 | 6976.32 | 0 | 0 | 0 | 0 |  | 81211.52
| Sr. Design Engineer | 120 | 0.5 | 11700 | 2 | 46800 | 2 | 46800 | 2 | 46800 | 0.5 | 12168 | 0.4 | 9734.4 | 0 | 0 | 0 | 0 |  | 174002.4
| Software Engineer | 122 | 0.25 | 5720 | 0.75 | 17160 | 1 | 22880 | 1 | 22880 | 0.25 | 5948.8 | 0.5 | 11897.6 | 0 | 0 | 0 | 0 |  | 86486.4
| Quality Control | 124 | 0.33 | 5834.4 | 0.33 | 5834.4 | 0.5 | 8840 | 0.5 | 8840 | 0.33 | 6067.776 | 1 | 18387.2 | 0 | 0 | 0 | 0 |  | 53803.776
| Design Engineer | 125 | 2 | 44200 | 1 | 22100 | 3 | 66300 | 3 | 66300 | 2 | 45968 | 1 | 22984 | 0 | 0 | 0 | 0 |  | 267852
| Associate Design Engineer | 127 | 2 | 36400 | 2 | 36400 | 3 | 54600 | 3 | 54600 | 2 | 37856 | 1 | 18928 | 0 | 0 | 0 | 0 |  | 238784
| Sr. Test Engineer | 130 | 0 | 0 | 0 | 0 | 1 | 23920 | 1 | 23920 | 1 | 24876.8 | 3 | 74630.4 | 0 | 0 | 0 | 0 |  | 147347.2
| Test Engineer | 135 | 0 | 0 | 0 | 0 | 2 | 45760 | 2 | 45760 | 4 | 95180.8 | 5 | 118976 | 0 | 0 | 0 | 0 |  | 305676.8
| Project Coordinator | 140 | 0.33 | 6349.2 | 0.33 | 6349.2 | 0.33 | 6349.2 | 0.33 | 6349.2 | 0.33 | 6603.168 | 0.33 | 6603.168 | 0 | 0 | 0 | 0 |  | 38603.136
| Configuration Management | 142 | 0.33 | 6349.2 | 0.33 | 6349.2 | 0.33 | 6349.2 | 0.33 | 6349.2 | 0.33 | 6603.168 | 0.33 | 6603.168 | 0 | 0 | 0 | 0 |  | 38603.136
| Business Manager | 150 | 0.33 | 6520.8 | 0.33 | 6520.8 | 0.33 | 6520.8 | 0.33 | 6520.8 | 0.33 | 6781.632 | 0.33 | 6781.632 | 0 | 0 | 0 | 0 |  | 39646.464
|  | Activity "B" Subtotal | 7.23 | 151413.6 | 8.43 | 180325.6 | 14.95 | 323367.2 | 14.95 | 323367.2 | 12.23 | 277527.744 | 13.85 | 320348.288 | 0 | 0 | 0 | 0 |  | 1576349.632
|  |  | 1Q06 |  | 2Q06 |  | 3Q06 |  | 4Q06 |  | 1Q06 |  | 2Q06 |  | 3Q06 |  | 4Q06 |  |  | TOTAL
WBS Level 2 |  | Labor | Equivalent | Direct | Equivalent | Direct | Equivalent | Direct | Equivalent | Direct | Equivalent | Direct | Equivalent | Direct | Equivalent | Direct | Equivalent | Direct |  | DIRECT
Activity | Labor Category | ID Code | People Rq'd | Cost | People Rq'd | Cost | People Rq'd | Cost | People Rq'd | Cost | People Rq'd | Cost | People Rq'd | Cost | People Rq'd | Cost | People Rq'd | Cost |  | COST
Activity | Project Manager | 100 | 1 | 28600 | 1 | 28600 | 1 | 28600 | 1 | 28600 | 1 | 29744 | 1 | 29744 | 0 | 0 | 0 | 0 |  | 173888
"C" | Sr. Systems Engineer | 110 | 1 | 23400 | 1 | 23400 | 1 | 23400 | 1 | 23400 | 1 | 24336 | 1 | 24336 | 0 | 0 | 0 | 0 |  | 142272
| Systems Engineer | 112 | 0.5 | 11180 | 0.7 | 15652 | 0.8 | 17888 | 0.8 | 17888 | 0.5 | 11627.2 | 0.3 | 6976.32 | 0 | 0 | 0 | 0 |  | 81211.52
| Sr. Design Engineer | 120 | 0.5 | 11700 | 2 | 46800 | 2 | 46800 | 2 | 46800 | 0.5 | 12168 | 0.4 | 9734.4 | 0 | 0 | 0 | 0 |  | 174002.4
| Software Engineer | 122 | 0.25 | 5720 | 0.75 | 17160 | 1 | 22880 | 1 | 22880 | 0.25 | 5948.8 | 0.5 | 11897.6 | 0 | 0 | 0 | 0 |  | 86486.4
| Quality Control | 124 | 0.2 | 3536 | 0.33 | 5834.4 | 0.5 | 8840 | 0.5 | 8840 | 0.33 | 6067.776 | 1 | 18387.2 | 0 | 0 | 0 | 0 |  | 51505.376
| Design Engineer | 125 | 1 | 22100 | 2 | 44200 | 3 | 66300 | 3 | 66300 | 1 | 22984 | 0.5 | 11492 | 0 | 0 | 0 | 0 |  | 233376
| Associate Design Engineer | 127 | 2 | 36400 | 2 | 36400 | 3 | 54600 | 3 | 54600 | 2 | 37856 | 1 | 18928 | 0 | 0 | 0 | 0 |  | 238784
| Sr. Test Engineer | 130 | 1 | 23920 | 0 | 0 | 1 | 23920 | 1 | 23920 | 1 | 24876.8 | 3 | 74630.4 | 0 | 0 | 0 | 0 |  | 171267.2
| Test Engineer | 135 | 0 | 0 | 0 | 0 | 2 | 45760 | 2 | 45760 | 2 | 47590.4 | 5 | 118976 | 0 | 0 | 0 | 0 |  | 258086.4
| Project Coordinator | 140 | 0.33 | 6349.2 | 0.33 | 6349.2 | 0.33 | 6349.2 | 0.33 | 6349.2 | 0.33 | 6603.168 | 0.33 | 6603.168 | 0 | 0 | 0 | 0 |  | 38603.136
| Configuration Management | 142 | 0.33 | 6349.2 | 0.33 | 6349.2 | 0.33 | 6349.2 | 0.33 | 6349.2 | 0.33 | 6603.168 | 0.33 | 6603.168 | 0 | 0 | 0 | 0 |  | 38603.136
| Business Manager | 150 | 0.33 | 6520.8 | 0.33 | 6520.8 | 0.33 | 6520.8 | 0.33 | 6520.8 | 0.33 | 6781.632 | 0.33 | 6781.632 | 0 | 0 | 0 | 0 |  | 39646.464
|  | Activity "C" Subtotal | 8.44 | 185775.2 | 10.77 | 237265.6 | 16.29 | 358207.2 | 16.29 | 358207.2 | 10.57 | 243186.944 | 14.69 | 345089.888 | 0 | 0 | 0 | 0 |  | 1727732.032
|  | PROJECT TOTAL | 22.9 | 488602.4 | 31.04 | 665433.6 | 48.7 | 1053582.4 | 47.7 | 1031482.4 | 35.04 | 795560.064 | 43.3 | 1004087.136 | 0 | 0 | 0 | 0 | 0 | 5038748
[18 empty] | Budgetary Minimum |  | 4282935.8
[18 empty] | Budgetary Maximum (NTE) |  | 6550372.4
LABOR | FORWARD PRICING DIRECT LABOR RATES
ID CODE | TITLE | 2010 | 2011 | 2012
100 | Project Manager | 55 | 57.2 | 59.488
110 | Sr. Systems Engineer | 45 | 46.8 | 48.672
112 | Systems Engineer | 43 | 44.72 | 46.5088
120 | Sr. Design Engineer | 45 | 46.8 | 48.672
122 | Software Engineer | 44 | 45.76 | 47.5904
124 | Quality Control | 34 | 35.36 | 36.7744
125 | Design Engineer | 42.5 | 44.2 | 45.968
127 | Associate Design Engineer | 35 | 36.4 | 37.856
130 | Sr. Test Engineer | 46 | 47.84 | 49.7536
135 | Test Engineer | 44 | 45.76 | 47.5904
140 | Project Coordinator | 37 | 38.48 | 40.0192
142 | Configuration Management | 37 | 38.48 | 40.0192
150 | Business Manager | 38 | 39.52 | 41.1008
| Projected Annual Rate Increase= | 4%
BUDGETARY COST ESTIMATING MODEL
How To Use This Model
The purpose of this model is to prepare typical project "budgetary cost estimates." It is a simplified model based solely on direct labor estimates and does not include cells for material, subcontract, or burdening costs (overhead, G&A, etc.).
Users of this model should replace "labor category" descriptions and ID codes to match those used by your company. Then, the "forward pricing labor rate" table, located at the bottom of the model should be updated to reflect your company's actual labor rates for each forecasted year. These are usually obtained from your financial department.
The model can be easily expanded to fit actual user needs and ultimately provides a "budgetary cost estimate range" based on the standards recommended by the American Association of Cost Engineers.

## Profit Model
Fill in white cells only. All others will be calculated automatically. | [5 empty] | YEAR
| Assumptions |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | TOTAL
MARKETING FORECAST
Average sales price per unit | 10% | per year |  |  | 4400 | 3960 | 3564 | 3207.6 | 2886.84 | 2598.156
Market size (units) |  |  |  |  | 10000 | 20000 | 40000 | 70000 | 40000 | 30000
Market share |  |  |  |  | 65% | 50% | 40% | 25% | 15% | 10%
Unit sales |  |  |  |  | 6500 | 10000 | 16000 | 17500 | 6000 | 3000
TOTAL PROJECTED SALES |  |  |  |  | 28600000 | 39600000 | 57024000 | 56133000 | 17321040 | 7794468 | 206472508
PRODUCT COSTS |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | TOTAL
Project Costs
Product Conception |  |  | 1: 300000 | 300000
Project Planning & Staffing |  |  | 1: 757000 | 757000
Product Design |  |  | 1: 720000 | 720000
Product Modeling |  |  | 1: 135000 | 135000
Manufacture First Unit |  |  | 2: 350000 | 350000
Test & Verification |  |  | 2: 250000 | 250000
Total Product Development Costs |  |  | 1912000 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 2512000
Product Support Costs |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | TOTAL
Cost per unit (production) | 5% | per year |  |  | 2000 | 1900 | 1805 | 1714.75 | 1629.0125 | 1547.5619 | 10596.3244
Total production cost |  |  |  |  | 13000000 | 19000000 | 28880000 | 30008125 | 9774075 | 4642685.625 | 105304885.625
Maintenance Costs |  |  |  |  | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 600000
General & Administrative Expense | 1% | of sales |  |  | 286000 | 396000 | 570240 | 561330 | 173210.4 | 77944.68 | 2064725.08
Overhead Expense | 5% | of sales |  |  | 1430000 | 1980000 | 2851200 | 2806650 | 866052 | 389723.4 | 10323625.4
Marketing expenses | 2% | of total sales |  |  | 572000 | 792000 | 1140480 | 1122660 | 346420.8 | 155889.36 | 4129450.16
Total Product Support Costs |  |  |  |  | 15388000 | 22268000 | 33541920 | 34598765 | 11259758.2 | 5366243.065 | 122422686.265
TOTAL PRODUCT COSTS |  |  | 1912000 | 600000 | 15388000 | 22268000 | 33541920 | 34598765 | 11259758.2 | 5366243.065 | 124934686.265
PROFITABILITY FORECAST |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | TOTAL
Profit before tax (PBT) |  |  | -1912000 | -600000 | 13212000 | 17332000 | 23482080 | 21534235 | 6061281.8 | 2428224.935 | 81537821.735
Return on investment (%) |  |  |  |  | 85.86% | 77.83% | 70.01% | 62.24% | 53.83% | 45.25%
Cumulative PBT (Cash Flow) |  |  | -1912000 | -2512000 | 10700000 | 28032000 | 51514080 | 73048315 | 79109596.8 | 81537821.735
|  |  | 8: Total Product Costs | 124934686.265
|  |  | 8: Total Product Sales | 206472508
|  |  | 8: Benefit/Cost Ratio | 1.6526
|  |  | 8: Total PBT | 81537821.735
|  |  | 8: Return on Investment | 65.26%
|  |  | 8: Return on Sales | 39.49%
Note on C10: These prices fall at a rate proportional to the rate of improvement in price-performance of a product's underlying technology. For example, semiconductor unit prices typically fall at a rate of 25% to 30% per year. Computer printers may decrease by 15% per year. Each market has its own underlying long-term price trend.
Note on C11: Projected market size is determined by the marketing department and is key to determining the overall profitability of a new product.
Note on C12: This is the expected number of units to be sold as a percentage of the total market size.
Note on C13: This is the expected number of units to be sold.
Note on C28: The "Cost per Unit" usually decreases because of the learning curve common in industry. Typical learning curve might produce cost drops of 5% to 15% for every doubling of volume. The latter is called an 85% learning curve. Manufacturing should be involved with projecting these costs.
Note on C31: This is usually applied as a percentage of sales and is typically obtained from the Finance Department. G&A expenses include the indirect expenses of company executives, attorneys, and in some cases, administrators.
Note on C32: This is usually applied as a percentage of sales. This percentage is usually obtained from the Finance Department. Overhead expenses typically include costs associated with facilities, employee benefits, security systems, insurance, and utilities.
Note on C33: This is usually applied as a percentage of sales. This percentage is usually obtained from the Finance Department.
Note on C36: Total Product Cost is the sum of the Total Product Development Costs and the Total Product Support Cost.
Note on C40: Profit before tax (PBT) is determined by subtracting the Total Product Cost from the Total Product Sales.
Note on M47: The Benefit/Cost ratio is determined by dividing the Total Product Sales (Benefits) by the Total Product Cost.
Note on M48: Total Profit Before Taxes is determined by subtracting the Total Product Costs from the Total Product Sales.
Note on M49: Return-on-Investment is determined by dividing the Total PBT by the Total Product Cost and is usually shown as a percent.
Note on M50: Return-on-Investment is determined by dividing the Total PBT by the Total Product Sales and is usually shown as a percent.
Profit Model

## KTA Model
Fill in unshaded cells only. Replace numbers & text with your own.
MUSTS |  | Product A |  | Go/No Go | Product B |  | Go/No Go | Product C |  | Go/No Go | Product A | P | S | P x S | Product B | P | S | P x S | Product C | P | S | P x S
Achieve an ROI of at least 30% |  |  | 30% | Go |  | 40% | Go |  | 35% | Go | May only get three of needed skilled people | 5 | 7 | -35 | Needed skills may not be available | 4 | 5 | -20 | New technology may create high risks | 2 | 4 | -8
[15 empty] | May have difficulty producing product | 5 | 5 | -25
0
0
[14 empty] | -35 |  |  |  | -45 |  |  |  | -8
WANTS | Weight | Info | Score | Weighted Score | Info | Score | Weighted Score | Info | Score | Weighted Score
Meets customer needs | 25 |  | 5 | 125 |  | 4 | 100 |  | 4 | 100
Favorable time-to-market (schedule) | 10 |  | 5 | 50 |  | 4 | 40 |  | 3 | 30
Minimal project cost | 5 |  | 5 | 25 |  | 3 | 15 |  | 4 | 20
Product can be easily modeled | 5 |  | 4 | 20 |  | 5 | 25 |  | 3 | 15
Minimal technology risks | 15 |  | 0 | 0 |  | 3 | 45 |  | 5 | 75
Predicted return-on-investment (ROI) | 25 |  | 1 | 25 |  | 5 | 125 |  | 3 | 75
Forecasted product reliability | 10 |  | 3 | 30 |  | 5 | 50 |  | 3 | 30
Producibility (can me made easily) | 5 |  | 5 | 25 |  | 3 | 15 |  | 4 | 20
|  |  |  | 0 |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  | 0 |  |  | 0
TOTAL | 100 |  | Weighted Score | 300 |  | Weighted Score | 415 |  | Weighted Score | 365
|  |  | Risk Factor | -35 |  |  | -45 |  |  | -8
|  |  | Adjusted Score | 265 |  | Adjusted Score | 370 |  | Adjusted Score | 357
Note on D32: Weights must come to a total of "100."
KEPNER-TREGOE ANALYSIS
KEPNER-TREGOE ANALYSIS
Risk Factor Calculations

## RAM Example
1 = Primary responsibility 2 = Must be consulted 3 = May be consulted 4 = Has approval authority
| Project | Systems | Proj. Controls | Project | Team | Manuf. | Marketing | Subcontract | Design | Configuration
PROJECT RESPONSIBILITIES | Manager | Engineer | Leader | Coordinator | Leaders | Manager | Specialists | Manager | Engineers | Manager
Define overall project goals | 1,4 | 2 | 2 | 3 | 3 | 2 | 2 | 3 | 3
Oversee the development of a project plan | 1,4 | 2 | 2 | 3 | 3 | 2 | 2 | 3 | 3
Develop a Work Breakdown Structure (WBS) | 2,4 | 2 | 1 | 3 | 3 | 2 | 2 | 3 | 3
Establish top-level project requirements | 1,4 | 2 | 2 | 3 | 3 | 2 | 2 | 3 | 3
Establish hardware specifications |  | 2,4 |  |  | 2,4 | 2,4 | 2,4 | 3 | 1,4
Establish software specifications |  | 2,4 |  |  | 2,4 | 2,4 | 2,4 | 3 | 1,4
Develop the project organization breakdown structure (OBS) | 1,4 | 2 | 2 |  | 3 | 3 | 3 | 3
Define overall project workscope | 1,4 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3
Develop the project responsibility allocation matrix (RAM) | 1,4 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3
Identify major project technical risks & develop mitigation plans | 2,4 | 1,4 | 3 | 3 | 2 | 2 | 2 | 2 | 3
Identify major project business risks & develop mitigation plans | 2,4 | 3 | 1,4 | 3 | 3 | 2 | 2 | 2 | 3
Conduct make-or-buy decision process | 1,4 | 2 | 2 |  | 3 | 3 | 3 | 2 | 3
Develop a project tracking system | 1,4 | 2 | 2 | 3 | 3 | 3 | 3 | 3
Identify major project milestones | 1,4 | 2 | 2 | 3 | 3 | 3 | 3 | 3
Develop a project reporting requirements | 1,4 | 2 | 2 | 3 | 3 | 3 | 3 | 3
Conduct regular project status reviews | 2,4 | 2 | 2 | 1 | 2 | 2 | 2 | 2 | 2
Prepare project budgets | 2,4 | 2 | 1,4 | 2 | 2 | 2 | 2 | 2 | 2
Develop the detailed project schedule | 2,4 | 2 | 2 | 1 | 2 | 2 | 2 | 2 | 2
Conduct designated product design reviews | 2,4 | 1,4 | 3 | 3 | 2 | 2 | 2 | 2 | 2
Customer point-of-contact | 1 | 2 | 2
Develop a project change-control system | 2,4 | 2 | 1,4 | 2 | 2 | 2 | 2 | 2 | 2
Chair the change-control board | 1,4 | 2 | 2
Identify and track all project baseline changes |  |  | 2 | 2 | 3 |  |  | 2 |  | 1
Coordinate change-control board activities |  |  |  | 2 | [5 empty] | 1
Manage subcontractors | 2,4 | 2 | 2 |  |  |  |  | 1 |  | 3
Develop a subcontract management plan | 4 | 3 | 4 | 3 |  |  |  | 1 |  | 3
Prepare a manufacturing plan | 2,4 | 2,4 |  | 3 | 3 | 1,4 |  |  | 3
Develop a team plan | 4 | 3 | 3 | 3 | 1 |  |  |  | 2
Develop a team RAM |  |  |  |  | 1
Provide regular team status |  | 2 |  | 2 | 1 |  |  |  | 2
Identify and monitor customer needs | 2,4 | 2,4 | 2,4 | 3 | 3 | 3 | 1,4 | 3 | 3
Responsibility Allocation Matrix

## Stochastic Duration Estimating
| Fill in the white cells--all other cells are automatically calculated. |  |  |  |  | Insert a start date below.
Activity | Optimistic | Most Likely | Pessimistic | Expected Time | Variance |  | Start Date = | 2010-01-01
No. | (o) | (m) | (p) | Te |  | Probability | Duration | End Date (7 d/wk) | End Date (5 d/wk)
1 | 0 | 0 | 0 | 0 | 0 | 10% | 0 | 2010-01-01 | 2010-01-01
2 | 0 | 0 | 0 | 0 | 0 | 15% | 0 | 2010-01-01 | 2010-01-01
3 | 0 | 0 | 0 | 0 | 0 | 20% | 0 | 2010-01-01 | 2010-01-01
4 | 0 | 0 | 0 | 0 | 0 | 25% | 0 | 2010-01-01 | 2010-01-01
5 | 0 | 0 | 0 | 0 | 0 | 30% | 0 | 2010-01-01 | 2010-01-01
6 | 0 | 0 | 0 | 0 | 0 | 35% | 0 | 2010-01-01 | 2010-01-01
7 | 0 | 0 | 0 | 0 | 0 | 40% | 0 | 2010-01-01 | 2010-01-01
8 | 0 | 0 | 0 | 0 | 0 | 45% | 0 | 2010-01-01 | 2010-01-01
9 | 0 | 0 | 0 | 0 | 0 | 50% | 0 | 2010-01-01 | 2010-01-01
10 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 2010-01-01 | 2010-01-01
11 | 0 | 0 | 0 | 0 | 0 | 60% | 0 | 2010-01-01 | 2010-01-01
12 | 0 | 0 | 0 | 0 | 0 | 65% | 0 | 2010-01-01 | 2010-01-01
13 | 0 | 0 | 0 | 0 | 0 | 70% | 0 | 2010-01-01 | 2010-01-01
14 | 0 | 0 | 0 | 0 | 0 | 75% | 0 | 2010-01-01 | 2010-01-01
15 | 0 | 0 | 0 | 0 | 0 | 80% | 0 | 2010-01-01 | 2010-01-01
16 | 0 | 0 | 0 | 0 | 0 | 85% | 0 | 2010-01-01 | 2010-01-01
17 | 0 | 0 | 0 | 0 | 0 | 90% | 0 | 2010-01-01 | 2010-01-01
|  |  | TOTAL | 0 | 0 | 95% | 0 | 2010-01-01 | 2010-01-01
Note on D9: Estimated cost/duration under ideal conditions.
Note on E9: Most likely cost/duration for a given project task.
Note on F9: Estimated cost/duration under worst case conditions.
Note on G9: Expected value equals (o+4m+p) divided by 6, for a normal distribution.
Note on H9: Variance is equal to p-o divided by 6 and the whole expression squared. See your student notebook.
Note on L10: Dates assume that all days are working days.
Note on M10: No holidays are assumed.
Stochastic Duration Estimating Model

## Time-Value Calculator
Present Value (PV) |  | n | Future Value (FV) | Future Value (FV) |  | n | Present Value (PV)
6210 | 0.1 | 4 | 9092.061 | 0 | 0 | 0 | 0
11300 | 0.1 | 3 | 15040.3 | 0 | 0 | 0 | 0
15380 | 0.1 | 2 | 18609.8 | 0 | 0 | 0 | 0
18680 | 0.1 | 1 | 20548 | 0 | 0 | 0 | 0
21186 | 0.1 | 0 | 21186 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72756 |  |  | 84476.161 |  |  |  | 0
Note on C6: Insert value in decimal form.
Note on C7: Insert value in decimal form.
Note on C8: Insert value in decimal form.
Note on C9: Insert value in decimal form.
Note on C10: Insert value in decimal form.
Note on C11: Insert value in decimal form.
Note on C12: Insert value in decimal form.
Note on C13: Insert value in decimal form.
Note on C14: Insert value in decimal form.
Note on C15: Insert value in decimal form.
Note on C16: Insert value in decimal form.
Note on C17: Insert value in decimal form.
Note on H6: Insert value in decimal form.
Note on H7: Insert value in decimal form.
Note on H8: Insert value in decimal form.
Note on H9: Insert value in decimal form.
Note on H10: Insert value in decimal form.
Note on H11: Insert value in decimal form.
Note on H12: Insert value in decimal form.
Note on H13: Insert value in decimal form.
Note on H14: Insert value in decimal form.
Note on H15: Insert value in decimal form.
Note on H16: Insert value in decimal form.
Note on H17: Insert value in decimal form.
Future Value Calculator
Present Value Calculator

## Stochastic Cost Estimating
Fill in the white cells
Fill in the white cells--all other cells are automatically calculated.
Activity | Optimistic | Most Likely | Pessimistic | Expected Cost | Variance
No. | (o) | (m) | (p) | Ce |  | Probability | Project Cost
1 | 0 | 0 | 0 | 0 | 0 | 10% | 0
2 | 0 | 0 | 0 | 0 | 0 | 15% | 0
3 | 0 | 0 | 0 | 0 | 0 | 20% | 0
4 | 0 | 0 | 0 | 0 | 0 | 25% | 0
5 | 0 | 0 | 0 | 0 | 0 | 30% | 0
6 | 0 | 0 | 0 | 0 | 0 | 35% | 0
7 | 0 | 0 | 0 | 0 | 0 | 40% | 0
8 | 0 | 0 | 0 | 0 | 0 | 45% | 0
9 | 0 | 0 | 0 | 0 | 0 | 50% | 0
10 | 0 | 0 | 0 | 0 | 0 | 55% | 0
11 | 0 | 0 | 0 | 0 | 0 | 60% | 0
12 | 0 | 0 | 0 | 0 | 0 | 65% | 0
13 | 0 | 0 | 0 | 0 | 0 | 70% | 0
14 | 0 | 0 | 0 | 0 | 0 | 75% | 0
15 | 0 | 0 | 0 | 0 | 0 | 80% | 0
16 | 0 | 0 | 0 | 0 | 0 | 85% | 0
17 | 0 | 0 | 0 | 0 | 0 | 90% | 0
|  |  | TOTAL | 0 | 0 | 95% | 0
Note on D5: Estimated cost/duration under ideal conditions.
Note on E5: Most likely cost/duration for a given project task.
Note on F5: Estimated cost/duration under worst case conditions.
Note on G5: Expected value equals (o+4m+p) divided by 6, for a normal distribution.
Note on H5: Variance is equal to p-o divided by 6 and the whole expression squared. See your student notebook.
Stochastic Cost Estimating Model

## BOE Form
No. | Direct Labor Hours | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
1 | [13 empty] | 0
2 | [13 empty] | 0
3 | [13 empty] | 0
4 | [13 empty] | 0
5 | [13 empty] | 0
6 | [13 empty] | 0
| Total Direct Labor Hours | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total Direct Labor Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No. | Direct Material/Other Costs | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
1 | [13 empty] | 0
2 | [13 empty] | 0
3 | [13 empty] | 0
4 | [13 empty] | 0
5 | [13 empty] | 0
6 | [13 empty] | 0
| Total Direct Material/Other Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No. | Total Costs | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | [13 empty] | 0
| Total Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Basis Of Estimate Calculations (Direct Labor)
1
2
3
4
5
6
Note on C14: A labor rate of $50 per hour was used for illustration purposes. For better accuracy, actual labor rates should be used.
Basis of Estimate

## Benefit-Cost Table
| Market Size | 150000
| Estimated Market Share | 10%
| Unit Sales Price | 300
| Projected Sales ($K) | 4500
| Total Project Cost ($K) | 970
| Production Cost | 1875
| Overhead/G&A | 45
| Total Profit Before Taxes ($K) | 1610
| Project B/C Ratio | 1.6598
WBS Level | WBS Element | Cost ($K) | % of TPC | Weight | B/C Ratio | Commments
1 | SYSTEM | 970 | 100% | 1 | 1.6598
2 | Segment 1.0 | 270 | 27.84% | 0.45 | 2.6833
3 | Subsystem 1.1 | 125 | 12.89% | 0.2 | 2.576
4 | Module 1.1.1 | 75 | 7.732% | 0.1 | 2.1467
4 | Module 1.1.2 | 50 | 5.155% | 0.1 | 3.22
3 | Subsystem 1.2 | 95 | 9.794% | 0.15 | 2.5421
4 | Module 1.2.1 | 40 | 4.124% | 0.05 | 2.0125
4 | Module 1.2.2 | 55 | 5.67% | 0.1 | 2.9273
3 | Subsystem 1.3 | 50 | 5.155% | 0.1 | 3.22
4 | Module 1.3.1 | 30 | 3.093% | 0.06 | 3.22
4 | Module 1.3.2 | 20 | 2.062% | 0.04 | 3.22
2 | Segment 2.0 | 220 | 22.68% | 0.3 | 2.1955
3 | Subsystem 2.1 | 75 | 7.732% | 0.05 | 1.0733
4 | Module 2.1.1 | 40 | 4.124% | 0.03 | 1.2075
4 | Module 2.1.2 | 35 | 3.608% | 0.02 | 0.92 | The cost for this element outweighs the benefit
3 | Subsystem 2.2 | 95 | 9.794% | 0.08 | 1.3558
4 | Module 2.2.1 | 65 | 6.701% | 0.05 | 1.2385
4 | Module 2.2.2 | 30 | 3.093% | 0.03 | 1.61
3 | Subsystem 2.3 | 50 | 5.155% | 0.04 | 1.288
4 | Module 2.3.1 | 15 | 1.546% | 0.03 | 3.22
4 | Module 2.3.2 | 35 | 3.608% | 0.01 | 0.46 | The cost for this element outweighs the benefit
2 | Segment 3.0 | 340 | 35.05% | 0.1 | 0.47353 | The cost for this element outweighs the benefit
3 | Subsystem 3.1 | 120 | 12.37% | 0.01 | 0.13417 | The cost for this element outweighs the benefit
| Module 3.1.1 | 70 | 7.216% | 0.005 | 0.115 | The cost for this element outweighs the benefit
| Module 3.1.2 | 50 | 5.155% | 0.005 | 0.161 | The cost for this element outweighs the benefit
3 | Subsystem 3.2 | 100 | 10.31% | 0.07 | 1.127
| Module 3.2.1 | 60 | 6.186% | 0.03 | 0.805 | The cost for this element outweighs the benefit
| Module 3.2.2. | 40 | 4.124% | 0.04 | 1.61
3 | Subsystem 3.3 | 120 | 12.37% | 0.02 | 0.26833 | The cost for this element outweighs the benefit
| Module 3.3.1 | 80 | 8.247% | 0.01 | 0.20125 | The cost for this element outweighs the benefit
| Module 3.3.2 | 40 | 4.124% | 0.01 | 0.4025 | The cost for this element outweighs the benefit
2 | Project Management | 140 | 14.43% | 0.15 | 1.725
3 | Project Coordination | 30 | 3.093% | 0.02 | 1.0733
3 | Configuration Mgt. | 40 | 4.124% | 0.04 | 1.61
3 | Systems Engineering | 70 | 7.216% | 0.09 | 2.07
Note on F20: "Weights" can be established from any of the following methods: a) Market surveys b) AHP pair-wise comparisons c) Conjoint analysis d) Customer inputs e) Delphi sessions with customer-knowledgable experts. The method used should relate "weights to identified customer needs, or requirements.
Note on F21: This value must always equal 1.0
Benefit/Cost Table
Commercial Product Project Example
"Weights" can be established from any of the following methods:
a) Market surveys
b) AHP pair-wise comparisons
c) Conjoint analysis
d) Customer inputs
e) Delphi sessions with customer-knowledgable experts.
The method used should relate "weights" to identified customer needs, or requirements.
The Benefit/Cost (B/C) ratio is equal to the "weight" times the total benefit (total profit before taxes) divided by the cost of the project element.

## Critical Path Crashing Tool
Sort table on "crash ratio" after the "Crash Project" values are inserted.
Fill In whire cells only |  | NORMAL PROJECT |  | CRASHED PROJECT |  | CRASH CALCULATIONS
Activity No. | Description | Time | Cost | Time | Cost | Allowable Crash | Crash Ratio | Project Duration | Cumulative Project Cost
[6 empty] | 0 | #DIV/0! | 0 | #DIV/0!
[6 empty] | 0 | #DIV/0! | 0 | #DIV/0!
[6 empty] | 0 | #DIV/0! | 0 | #DIV/0!
[6 empty] | 0 | #DIV/0! | 0 | #DIV/0!
[6 empty] | 0 | #DIV/0! | 0 | #DIV/0!
[6 empty] | 0 | #DIV/0! | 0 | #DIV/0!
[6 empty] | 0 | #DIV/0! | 0 | #DIV/0!
[6 empty] | 0 | #DIV/0! | 0 | #DIV/0!
[6 empty] | 0 | #DIV/0! | 0 | #DIV/0!
[6 empty] | 0 | #DIV/0! | 0 | #DIV/0!
[6 empty] | 0 | #DIV/0! | 0 | #DIV/0!
[6 empty] | 0 | #DIV/0! | 0 | #DIV/0!
[6 empty] | 0 | #DIV/0! | 0 | #DIV/0!
|  | 0 | 0 | 0 | 0
Note on D24: This is the total remaining time before crashing the critical path.
Note on E9: These are the times and costs for each task on the project's critical path, before they have been crashed.
Note on E24: This is the total cost of all critical path activities before crashing the critical path.
Note on G24: This is the total remaining time if all of the critical path activities are crashed.
Note on H24: This is the total cost of all critical path activities after crashing the critical path.
Project Critical-Path Crashing Table

## Risk Analysis
| Triple Constraint Aspect | Technical | Schedule | Cost | Total
| Priority Weight | 0 | 0 | 0 | 0
| Fill in white cells only |  | Technical |  |  | Schedule |  |  | Cost |  | TOTAL
No. | Risk Description | P | C | WRF | P | C | WRF | P | C | WRF | WRF
1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on G6: Must equal 1.00
Weighted Risk Factor Analysis

## Zone Tracking Method
45%
Fill in white cells only.
Week No. | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Schedule Events-Planned
Schedule Events-Actual
Variance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Schedule Variance (%) | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Labor Hours-Planned
Labor Hours-Actual
Variance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost Variance (%) | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Project Tracking - Zone Method

## Earned-Value Method
Fill in white cells only.
Week No. | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Planned Value (PV)-Cumulative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual Cost (AC)-Cumulative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Earned Value (EV)-Cumulative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPI | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
CPI | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
If font size is too small on the graph below increase its size for better viewing.
Fill in white cells only.
Estimate at Completion Analysis
Week No. |  | EAC= | #VALUE!
Total EV= | 0 | TCPIEAC= | #VALUE!
Total AC= | 0 | TCPIBAC= | #VALUE!
Estimate to Complete (ETC)= |  | VAC= | #VALUE!
Budget at Completion (BAC)= |  | VAC (%)= | #VALUE!
Project Tracking - Earned Value Method

## Control Staff Size
For projects over $2 Million:
|  |  |  | Estimated Total Project Cost = | 5000000
|  |  |  | Estimated annual labor rate ($/year) for "controls" personnel = | 45000
|  |  |  | Estimated project duration (years) = | 2.5
For projects under $2 Million:
|  |  |  | Estimated Total Project Cost (<$2M) = | 1400000
|  |  |  | Estimated annual labor rate ($/year) for "controls" personnel = | 45000
|  |  |  | Estimated project duration (years) = | 2.5
TABLE 1 - PROJECT CONTROL STAFF
| Budget for Controls Staff |  | Number of Equivalent People |  | Hours per Week
| Minimum | Maximum | Minimum | Maximum | Minimum | Maximum
Projects Over $2 Million | 50000 | 80000 | 1.1111 | 1.7778 | 44.4444 | 71.1111
Rule of Thumb Method | 40000 | 80000 | 0.88889 | 1.7778 | 35.5556 | 71.1111
Projects Under $2 Million | 22400 | 44800 | 0.49778 | 0.99556 | 19.9111 | 39.8222
Note on C20: The minimum and maximum values can extrapolated from the graph in the "Project Control Techniques" section of the student notebook based on a given TPC.
Note on C21: The Rule of Thumb method is based on using a minimum of 2% and a maximum of 4% when calculating the size of the Project Controls Staff.
Note on C22: This is for projects having a Total Project Cost of less than $2 Million. The numbers in this row are NOT applicable for projects over $2 Million.
Note on D22: This is for projects having a Total Project Cost of less than $2 Million. The numbers in this row are NOT applicable for projects over $2 Million.
Note on E22: This is for projects having a Total Project Cost of less than $2 Million. The numbers in this row are NOT applicable for projects over $2 Million.
Note on F22: This is for projects having a Total Project Cost of less than $2 Million. The numbers in this row are NOT applicable for projects over $2 Million.
Note on G22: This is for projects having a Total Project Cost of less than $2 Million. The numbers in this row are NOT applicable for projects over $2 Million.
Note on H8: Insert the estimated total project cost (TPC).
Note on H9: This is the estimated annual wage for a Project Control Staff person (coordinators, business managers, configuration managers, etc.)
Note on H10: Insert the duration of the project in years (1.2, 1.5, 2.0, etc).
Note on H13: Insert the estimated total project cost (TPC).
Note on H14: This is the estimated annual wage for a Project Control Staff person (coordinators, business managers, configuration managers, etc.)
Note on H15: Insert the duration of the project in years (1.2, 1.5, 2.0, etc).
Note on H22: This is for projects having a Total Project Cost of less than $2 Million. The numbers in this row are NOT applicable for projects over $2 Million.
Note on I18: Based on a 40-hour week for an "equivalent person."
Note on I22: This is for projects having a Total Project Cost of less than $2 Million. The numbers in this row are NOT applicable for projects over $2 Million.
DETERMINING THE SIZE OF THE PROJECT CONTROL STAFF
INSTRUCTIONS
1. Fill in the "Estimated Total Project Cost" (Cell H7).
2. Fill in the "Estimated annual labor rate" (Cell H8).
3. Fill in the "Estimated project duration" (Cell H9).
Note: For projects with an "estimated total project cost" less than $2 Million, use the input cells located below Table 1.
Table 1 will calculate the size of the project control staff needed for the project.